## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | Does Space Affect Earth’s Weather? |  | COMPANY NAME |  |  | University of Minnesota
PROJECT PARTICIPANTS |  | Rahul Ughade, Andy Hartman, Max Beehler, Jamie Reetz |  | DATE |  |  | 2019-03-25
PHASE |  |  | DETAILS
|  |  |  | 2019-03-21 | 2019-03-22 | 2019-03-23 |  | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04
1 | Project Conception and Initiation |  | - Find dataset | Find dataset - Max | [16 empty] | PROJECT END
|  |  | - Project Proposal |  |  | Project Proposal
|  |  | - Initiation |  |  | Google Drive, Slack channel, Github
2 | Project Definition and Planning |  | - Data Flow Architecture |  |  | Rahul
|  |  | - System Architecture Design | [6 empty] | Team
|  |  | - Work Breakdown Schedule | [6 empty] | Rahul
|  |  | - Gantt Chart | [5 empty] | Rahul
|  |  | - Task Assignment | [6 empty] | Team
3 | Project Development |  | - Import data to MongoDB | [6 empty] | Andy
|  |  | - Create RESTful API for data | [6 empty] | Jamie
|  |  | - Create Flask App | [6 empty] | Rahul + Andy + Jamie
|  |  | - Create HTML page | [8 empty] | Rahul
|  |  | - Create visualizations | [8 empty] | Max
4 | Project Review and Deployment |  | Review API call | [13 empty] | Team
|  |  | Review visualizations | [13 empty] | Team
|  |  | - Review HTML code | [13 empty] | Team
|  |  | - Combine all codes | [13 empty] | Rahul
5 | Project Close |  | - Upload final code to Git | [16 empty] | Rahul
|  |  | Presentation | [16 empty] | Team
|  |  | - Report | [16 empty] | Team

## Deliverables
Sr No | Task | Resources
1 | Conceptual design of backend
2 | Conceptual design of frontend
3 | Import data from NASA api to MongoDB | Database: fireballdb, Collection: fireballs
4 | Develop RESTful API for MongoDB data | https://gist.github.com/leon-sleepinglion/97bfd34132394e23ca5905ec730f776a
5 | Create HTML page for visualization
6 | Develop javascript app to render data to HTML page
7 | Use leaflet to display geospatial data
8 | Merge codes
9 | Test application
10 | Deploy application to git
11 | Deploy application to heroku