## Project Timeline
PROJECT TIMELINE
PROJECT TITLE |  | Does Space Affect Earth’s Weather? |  | COMPANY NAME |  |  | University of Minnesota
PROJECT PARTICIPANTS |  | Rahul Ughade, Andy Hartman, Max Beehler, Jamie Reetz |  | DATE |  |  | 2019-03-25
PHASE |  |  | DETAILS
|  |  |  | 2019-03-21 | 2019-03-22 | 2019-03-23 |  | 2019-03-24 | 2019-03-25 | 2019-03-26 | 2019-03-27 | 2019-03-28 | 2019-03-29 | 2019-03-30 | 2019-03-31 | 2019-04-01 | 2019-04-02 | 2019-04-03 | 2019-04-04
1 | Project Conception and Initiation |  | - Find dataset | Find dataset - Max | [15 empty] | PROJECT END
|  |  | - Project Proposal |  |  | Project Proposal
|  |  | - Initiation |  |  | Google Drive, Slack channel, Github
2 | Project Definition and Planning |  | - Data Flow Architecture |  |  | Rahul
|  |  | - System Architecture Design | [6 empty] | Team
|  |  | - Work Breakdown Schedule | [6 empty] | Rahul
|  |  | - Gantt Chart | [5 empty] | Rahul
|  |  | - Task Assignment | [6 empty] | Team
3 | Project Development |  | - Import data to MongoDB
- Create RESTful API for data
- Create Flask App
- Create HTML page
- Create visualizations
4 | Project Review and Deployment |  | Review API call
Review visualizations
- Review HTML code
- Combine all codes
5 | Project Close |  | - Upload final code to Git
- Deploy app to heroku
- Report